## inputs
Project abbreviation | RCT
Year | 2026
Goals | Baseline
Feature enhancement
Architecture

## Roadmap_items
ID | Name | Goal | Description | Acceptance Criteria | Start | End | PD | Cost
RCT-2026-001 | Baseline UI, UX & QOL improvements | Baseline | Baseline item to cover any continuous improvements to UI, UX and QOL. | - | 01.01.2026 | 31.12.2026 |  | 0
RCT-2026-002 | Jenkins Integration for Deployments | Feature enhancement | Be able to trigger deployment for a single application from RCT. Plan architecture to support application packages (multiple apps at once). |  |  |  |  | 0
RCT-2026-003 | Deprecate ETCD in favor of MongoDB | Architecture | RCT currently employs both ETCD and MongoDB. Deprecate ETCD to only use MongoDB to simplify deployment and improve performance/stability. |  | 01.01.2026 | 20.02.2026 |  | 0
RCT-2026-004 | Improve Rollout/Restart Robustness | Architecture | Make the architecture more robust to not have dependencies on the startup/restart order of components during RCT deployment. |  |  |  |  | 0
RCT-2026-005 | Automate RCT's Own Production Deployments | Feature enhancement | Use the RCT project as a PoC for automated production deployments (Staged: PR -> Hooks -> Rollback -> Full Auto). |  | 01.02.2026 | 30.04.2026 |  | 0
RCT-2026-006 | EAI Cockpit Deprecation | Baseline | Deprecate the legacy EAI Cockpit tool, migrating its functionalities to modern platforms like RCT. |  |  |  |  | 0
RCT-2026-007 | [7 empty] | 0
RCT-2026-008 | [7 empty] | 0
RCT-2026-009 | [7 empty] | 0
RCT-2026-010 | [7 empty] | 0